## Slide 1
Maverick Loyalty
Launch Checklist
What's left to take CustomerConnect from dev build to live product
Prepared for Maverick Telecom

## Slide 2
Where we are today
Done
Email + phone sign-up with a single 6-digit verification code
4-tier loyalty system (Starter, Explorer, Champion, Elite)
Receipt OCR (Tesseract) and MTN tax-invoice processing
Admin dashboard with role-based access control
Security hardening: bcrypt, rate limits, CSRF, HTTP-only sessions
Still to do
Email delivery to real customers (SendGrid)
Production database migration
Account recovery for lost email/phone
Legal pages and branding polish
Real-device QA, deploy, and go-live

## Slide 3
The 10 steps to launch
One slide per step. Each step says what it is, why it matters, and what 'done' looks like.
Step 1
Email delivery
Step 2
Production database
Step 3
Account recovery
Step 4
Legal & content
Step 5
Branding polish
Step 6
Real-device QA
Step 7
Admin & catalogue
Step 8
Deploy & domain
Step 9
Monitoring & backups
Step 10
Go-live announcement

## Slide 4
STEP 1
of 10
Email delivery
WHAT
Connect SendGrid (or another email provider) so verification codes land in real inboxes, not just the server log. Replace the plain text email with a branded HTML template in Maverick colours. Send a one-time welcome email after a customer verifies.
WHY IT MATTERS
Right now the verification code only prints to the dev console — no real customer can sign up. Email is the front door to the whole product.
DONE LOOKS LIKE
A new customer receives a branded email within seconds, enters the code, and is logged in. A welcome email follows.

## Slide 5
STEP 2
of 10
Production database
WHAT
Apply the new schema (is_verified, email_verifications, unique index on transactions) to the production database before the first deploy. Decide what to do with users already in the dev database — typically mark them all as verified so nobody is locked out.
WHY IT MATTERS
Without the migration the live app will crash on sign-up. Without the backfill, existing testers get stuck at the verification screen.
DONE LOOKS LIKE
Production schema matches dev. Existing users can still log in. No 'column does not exist' errors in the logs.

## Slide 6
STEP 3
of 10
Account recovery
WHAT
Decide and build what happens when a customer loses access to their email or phone. Minimum: an admin can reset a user's email or phone from the admin dashboard, and the change is written to the audit log.
WHY IT MATTERS
Lost-access tickets are the #1 support cost for any loyalty programme. Having a clear path on day one prevents stuck customers and angry calls.
DONE LOOKS LIKE
Support can change a verified contact in under a minute. The change is logged and reversible.

## Slide 7
STEP 4
of 10
Legal & content pages
WHAT
Add Privacy Policy, Terms of Service, and a basic Help / FAQ page. Link them from the footer and from the 'by signing up you agree to…' line on the registration form. Get the wording reviewed by Maverick legal before publishing.
WHY IT MATTERS
POPIA (South Africa's privacy law) requires a published privacy policy before you collect personal data. Customers also need to know what they're agreeing to.
DONE LOOKS LIKE
Three pages live, linked from every page footer and the sign-up form. Legal has signed off on the wording.

## Slide 8
STEP 5
of 10
Branding polish
WHAT
Walk every page on mobile and desktop. Confirm logo, colours, fonts and tone match Maverick's brand kit. Check empty states look intentional, error messages are friendly, and loading states are visible.
WHY IT MATTERS
Customers judge trust in the first 5 seconds. A loyalty programme that looks like a developer demo loses sign-ups before the value is even explained.
DONE LOOKS LIKE
Every page passes a side-by-side visual review against Maverick's brand kit. No placeholder text remains.

## Slide 9
STEP 6
of 10
Real-device QA
WHAT
Test the full flow on a real Android phone, a real iPhone, and a desktop browser: sign up, receive the email, enter the code, upload a real MTN till slip or PDF invoice, see points, redeem a reward, log out, log back in, forgot password.
WHY IT MATTERS
Browser dev tools lie. Real cameras, real keyboards, and real network conditions catch the bugs that ship to thousands of customers.
DONE LOOKS LIKE
The end-to-end flow works on all three devices. Anything that broke has been fixed and re-tested.

## Slide 10
STEP 7
of 10
Admin & catalogue
WHAT
Create the first real super-admin account for Maverick and remove any test admins. Load the real rewards catalogue, real MTN packages, and real point-earning rules.
WHY IT MATTERS
Launching on placeholder rewards is worse than not launching — customers earn points they cannot spend on anything they want.
DONE LOOKS LIKE
Maverick's chosen admin can sign in. The rewards catalogue, packages, and earning rules match what marketing has approved.

## Slide 11
STEP 8
of 10
Deploy & domain
WHAT
Publish the app via Replit Deployments. If Maverick has a domain (e.g. loyalty.maverick.co.za), connect it and verify HTTPS. Set production secrets (DATABASE_URL, SESSION_SECRET, SendGrid key) in the deployment environment.
WHY IT MATTERS
Until it's deployed on a Maverick URL, it isn't a product — it's a prototype.
DONE LOOKS LIKE
The app is live on the chosen URL, HTTPS works, all secrets are set, and the production sign-up flow completes end-to-end.

## Slide 12
STEP 9
of 10
Monitoring & backups
WHAT
Confirm the deployment logs are accessible and you know how to read them. Set up a regular automated backup of the production Postgres database so you can recover from a bad deploy or data loss.
WHY IT MATTERS
Things will break in production — what matters is how quickly you see it and how cleanly you can roll back.
DONE LOOKS LIKE
Logs are reachable in two clicks. A nightly database backup exists and a test restore has been done.

## Slide 13
STEP 10
of 10
Go-live announcement
WHAT
Send the launch email to Maverick customers and update the Maverick website with a link to the loyalty portal. Coordinate with marketing on timing and messaging.
WHY IT MATTERS
A launch nobody knows about is the same as no launch.
DONE LOOKS LIKE
The announcement is sent. The Maverick website links to the loyalty portal. Sign-ups start arriving.

## Slide 14
Ready when you are.
Pick a step and we'll start.
Recommended order: 1 → 2 → 7 → 4 → 8 → 3 → 5 → 6 → 9 → 10