## Slide 1
CustomerConnect
Maverick Telecom Loyalty Program — Two-Week Launch Plan
Prepared 20 July 2026 · Target launch: within 10 working days

## Slide 2
Where We Are Today
Core product is built and tested: points, 4-tier system, receipt scanning, rewards, redemptions
Dual sign-in live: email + password and SA mobile (+27)
Admin dashboard complete with role-based access and full audit log (with undo)
Security hardened: encrypted passwords, rate limiting, CSRF protection, secure sessions
POPIA-aligned Privacy Policy & Terms of Service drafted and linked from every page
Sign-up consent recorded per user with timestamp and policy version
Help & FAQ page live with search and 21 answered questions

## Slide 3
Week 1 · Days 1–2 — Close Open Technical Items
Create the Maverick super-admin account (Loyalty@mavericktelecom.co.za)
Wire up SendGrid so verification codes, password resets and welcome emails send for real
Replace placeholder contact details: support email, support phone, privacy@/legal@ addresses
Dependency: SendGrid API key and super-admin password from Maverick

## Slide 4
Week 1 · Days 3–5 — Legal Submission & Regression Pass
Days 3–4: Export Privacy Policy and Terms to PDF; submit to Maverick's lawyers with cover letter
Days 3–4: Add one-time 'Accept Terms' popup for phone sign-ins (email path already covered)
Day 5: Full end-to-end test — register → verify → upload receipt → earn points → redeem
Day 5: Admin dashboard test — user management, audit log, undo, analytics
Day 5: Mobile walkthrough on a real phone
The legal pack must go out this week — lawyer turnaround gates Week 2

## Slide 5
Week 2 — Legal Feedback, Publish, Go Live
Days 6–8: Apply lawyer feedback to policies; bump terms version for re-acceptance
Day 9: Publish to production (database schema applies automatically)
Day 9: Verify live URL — sign-up, sign-in, receipt upload, admin login
Day 9: Connect custom domain if desired (e.g. loyalty.mavericktelecom.co.za)
Day 10: Test deployed app end-to-end as a brand-new customer
Day 10: Confirm real emails arrive; hand over super-admin credentials and admin guide

## Slide 6
What We Need From Maverick
Super-admin password (account creation is otherwise ready to go)
SendGrid account + API key (free tier is fine to start)
Real contact details: support email, support phone, Information Officer name
Legal pack sent to lawyers in Week 1 — the only external dependency

## Slide 7
Risks & Fallback
Main risk: lawyer turnaround.
Everything else is within our control and fits comfortably in two weeks
Fallback: launch with current POPIA-aligned drafts; when final legal wording lands, bump the terms version and users re-accept on next sign-in
No data or feature risk — the platform is feature-complete and regression-tested before publish

## Slide 8
Timeline at a Glance
Days | Milestone
1–2 | Super-admin, SendGrid email, real contact details
3–4 | Legal pack submitted · phone-consent popup
5 | Full regression pass (web + mobile + admin)
6–8 | Lawyer feedback applied, terms version bumped
9 | Publish to production · domain connected
10 | Live verification · handover · LAUNCH